## Instructions
Your Name: | Andrew LeCain
Instructions
Enter your name above.
At the end of each week:
Under "Accomplished this week"
Make sure planned activities from last week copied correctly with estimated times
Fill in the actual amount of time spent on each activity and indicate whether it is done.
Add any other activities you worked on this week
Teams seem to relate better to times in hours down to the 1/4 hour, but feel free to use minutes if that has more meaning to you.
Under "Planned for next week"
Enter unfinished activities from this week that you will continue next week
Enter other planned activites for next week
Estimate the time you will spend on each activity. Estimate your time in minutes or hours down to the 1/4 hour.
Activities and estimates will copy to next week's accomplished section
Under "Issues"
Enter any unexpected problems you encountered
Enter any issues that require discussion with your team

## Week 7
Research Project - Week 1
Accomplished this week
Done? | ACT |  | Activity
X | 2 |  | Mechanical assembly of single motor
X | 2.5 |  | Initial electrical testing of optical encoder
X | 3 |  | Wiring and electrical testing of motor controller IC
| 7.5 |  | TOTAL TIME
Planned for next week
|  | EST | Activity
|  | 2 | Write wheel encoder stub/get working on QNX
|  | 3 | Refactor wheel encoder driver
|  | 2 | PWM output for motor control initial pass
|  | 2 | Control signals for motor controller
|  | 1 | Test/debug PWM output and motor control
|  | 3 | tentative: first pass on servo mode for motor
|  | 2 | Mechanical assembly of second motor
|  | 2 | Chassis construction
|  | 17 | TOTAL TIME
Issues
Need to get the other motor
Need to wire the accelerometer (should get here today)
need to decide on chassis design

## Week 8
Research Project - Week 2
Accomplished this week
Done? | ACT | EST | Activity
X | 2 | 2 | Write wheel encoder stub/get working on QNX
X | 3 | 3 | Refactor wheel encoder driver
X | 2 | 2 | PWM output for motor control initial pass
X | 2 | 2 | Control signals for motor controller
X | 1 | 1 | Test/debug PWM output and motor control
| 0 | 3 | tentative: first pass on servo mode for motor
X | 1.5 | 2 | Mechanical assembly of second motor
| 0 | 2 | Chassis construction
| 11.5 | 17 | TOTAL TIME
Planned for next week
|  | EST | Activity
|  | 2 | Chassis Construction
|  | 3 | Integrate Motor and PID (servo mode)
|  | 1 | First pass on accelerometer
|  | 2 | Refactor accelerometer
|  | 2 | First pass on PID control structure
|  | 4 | tentative: integrate accelerometer and PID (first pass balancing)
|  | 14 | TOTAL TIME
Issues

## Week 9
Research Project - Week 3
Accomplished this week
Done? | ACT | EST | Activity
X | 3 | 2 | Chassis Construction
|  | 3 | Integrate Motor and PID (servo mode)
X | 1 | 1 | First pass on accelerometer
X | 2 | 2 | Refactor accelerometer
X | 2 | 2 | First pass on PID control structure
| 2 | 4 | tentative: integrate accelerometer and PID (first pass balancing)
| 10 | 14 | TOTAL TIME
Planned for next week
|  | EST | Activity
|  | 3 | Integrate accelerometer and PID (first pass balancing)
|  | 3 | integrate motor and PID (servo mode)
|  | 2 | Tune PID (balancing)
|  | 2 | Tune PID (servo)
|  | 10 | TOTAL TIME
Issues
Didn’t get as much done on PID as I would have liked

## Week 10
Research Project - Week 4 to end
Accomplished this week
Done? | ACT | EST | Activity
|  | 3 | Integrate accelerometer and PID (first pass balancing)
|  | 3 | integrate motor and PID (servo mode)
|  | 2 | Tune PID (balancing)
|  | 2 | Tune PID (servo)
| 0 | 10 | TOTAL TIME
Planned for next week
|  | EST | Activity
|  | 0 | TOTAL TIME
Issues

## Example
Research Project - Week n
Accomplished this week
Done? | ACT | EST | Activity
Y | 1 | 1 | Discussed ideas for project goals
Y | 1.25 | 0.5 | Prepared project feature and task list
Y | 0.5 | 0.5 | Meeting with instructor
Y | 5.25 | 4 | Looked at driver library features and selected one
Y | 2 | 2 | Coded examples to access data acquisition hardware
| 10 | 8 | TOTAL TIME
Planned for next week
|  | EST | Activity
|  | 2 | Regular team meeting
|  | 0.5 | Meeting with instructor
|  | 1 | Write draft synopsis with Kate
|  | 4 | Look for webservices tutorials and work through them
|  | 2.5 | Work with Adam to make list of requirements questions
|  | 10 | TOTAL TIME
Issues
Hard disk on my computer died, had to restore from backup
Team is having trouble finding time to meet together
May need help coding error-handling subsystem